## Planning
Pipeline step | Task name | Est. (h) | Log. (h) | Notes
Pre-Production | Prototype shaders | 16 | 14 | Hatched and outline work, keep 4 hours for after feedback
| Reference: Composition | 2
| Reference: Buildings | 2
| Blockout scene | 8 |  | Put in more time than last exercise
Production: Assets | Rocks: sculpt, bake, texture | 12
| Terrain: design, texture | 8
| Vegetation: model | 4
| Vegetation: shaders | 8
| Modular building: model | 16
Post-Processing | Lighting | 4
| Performance check | 8
| PPVolume | 8
TOTAL |  | 96 | 14 | 82
TODO

## Log
Date | #Time (h) | Task | Note